{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Monthly"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Monthly","index":0,"n_rows":16,"n_cols":105,"rows_kept":16,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[]
["PROGRAMME - Portal Building"]
[]
[null,null,"Week",{"$nulls":43},"Week"]
[null,null,1,null,2,null,3,null,4,null,5,null,6,null,7,null,8,null,9,null,10,null,11,null,12,null,13,null,14,null,15,null,16,null,17,null,18,null,19,null,20,null,21,null,22,null,23,null,24,null,25,null,26,null,27,null,28,null,29,null,30,null,31,null,32,null,33,null,34,null,35,null,36,null,37,null,38,null,39,null,40,null,41,null,42,null,43,null,44,null,45,null,46,null,47,null,48,null,49,null,50,null,51,null,52]
["Portal Building ","No. of Days"]
[]
[]
["Site set up"]
["Removal of x3 generators "]
["Internal strip out works prior to demolition "]
["Demolition of stuctures down to floor slab level"]
["To break out and grub up floor slab and footings to site "]
["To crush hardcore materials and lay to building footprint"]